## PRODUCT BACKLOG
PRODUCT BACKLOG
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Display menu screen on program start | Menu | M
1 | Menu with "start game" and "exit" buttons | Menu | M
2 | Show the rules of the game when needed by user | Menu or Turn | M
3 | Change current player after the end of the turn | Turn | M
4 | Display game board | Init | M
5 | Display which player is playing the current turn | Turn | M
6 | Display the main deck cards | Cards | M
7 | Display the special deck cards | Cards | M
8 | Show win screen if current player has destroyed all enemy ships | End | M
9 | "Go back to menu" button is displayed in the win screen | End | S
10 | Current player can pause and resume the game | Turn | S
11 | Produce sound for throw of a dice / moving pawn / win screen / special actions | Turn | W
12 | Display dice throw / moving pawn with an animation | Turn | C
13 | Menu extended with "settings" button (for example, containing screen resolution, audio volume, …) | Menu | C
14 | Save current state of the game in a database | Turn | M
15
16
17
18
19
20
21
22
23
24

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
EXAMPLE
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a player I want to start the game from the menu, so that I can play it. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on start button, init game | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on game start - Clicks on the button area make the screen change (to init phase)
1 | As a player I want to quit the program from the menu, so that I can stop playing. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on exit button, quit program | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on quit program - Clicks on the button area make the program quit